## Sheet1
Friendship Walk Weekly Timeline
|  |  | Friendship Walk: | Pleasantville | Goal Metrics
[5 empty] | Teams | 100
|  |  | Event Date: | 2018-04-21 | Participants | 1000
|  |  | Staff Partner: | Jane Doe | Sponsorship | 20000
|  |  | Event Chair | John Smith | Fundraising | 80000
|  |  | Co-Chair: | Suzy Q | Total Revenue | 100000
Months Prior | Weeks Prior | Days Prior | Target Date | Task | Responsible Party | Status
| 51 |  | 2018-04-21 | Friendship Walk Chair recruited | Staff Partner/Event Chair
| 48 | 334 | 2017-05-22 | Secure Walk location and date | Staff Partner/Event Chair
| 47 | 327 | 2017-05-29 | Submit website ticket | Staff Partner
| 46 | 320 | 2017-06-05 | Complete Volunteer Commitment Form with Event Chair | Staff Partner/Event Chair
| 45 | 313 | 2017-06-12 | Train Friendship Walk Event Chair | Staff Partner/Event Chair
| 44 | 306 | 2017-06-19 | Plan Leadership Luncheon to identify potential event leadership - determine: invitees, date, time, venue, etc. | Staff Partner/Event Chair
| 43 | 299 | 2017-06-26 | Review which Friendship Walk Committee members are returning from last year and which ones need to be filled | Staff Partner/Event Chair
| 43 | 299 | 2017-06-26 | Schedule one-on-ones with prospect Friendship Walk Committee Chairs | Staff Partner/Event Chair
| 43 | 299 | 2017-06-26 | Complete Sphere of Influence for prospect Friendship Walk Committee members | Staff Partner/Event Chair
| 43 | 299 | 2017-06-26 | Complete Community Guide to evaluate growth opportunities | Staff Partner/Event Chair
| 43 | 299 | 2017-06-26 | Mail/deliver Leadership Luncheon invites (4 weeks prior to event) | Staff Partner/Event Chair
| 42 | 292 | 2017-07-03 | Begin Past Team Tracking Spreadsheet | Team Retention Chair
| 42 | 292 | 2017-07-03 | Release Monthly Team Touch | Team Recruitment/Team Retention Chair
| 42 | 292 | 2017-07-03 | Event Co-Char in place, Volunteer Commitment Form signed | Staff Partner/Event Chair
| 42 | 292 | 2017-07-03 | Sponsorship Chair in place, Volunteer Commitment Form signed | Staff Partner/Event Chair
| 42 | 292 | 2017-07-03 | Review & test website. Submit ticket for any issues or updates that need to be made | Staff Partner
| 40 | 278 | 2017-07-17 | Finalize sponsorship packages/levels | Staff Partner/Sponsorship Chair
| 40 | 278 | 2017-07-17 | Develop target list for new sponsors | Sponsorship Chair
| 40 | 278 | 2017-07-17 | Develop media sponsorship proposals | Staff Partner/Publicity Chair
| 39 | 271 | 2017-07-24 | Hold last year sponsorship proof of performance meetings | Sponsorship Chair
| 39 | 271 | 2017-07-24 | Reminder calls to Leadership Luncheon invitees (1-2 days prior to event) | Event Chair/Co-Chair
| 39 | 271 | 2017-07-24 | Host Leadership Luncheon (9 months prior to Walk day) | Event Chair/Co-Chair
| 39 | 271 | 2017-07-24 | Plan team touch activities for monthly team touches | Staff Partner/Team Retention Chair
| 38 | 264 | 2017-07-31 | Release Monthly Team Touch | Team Retention Chair
| 37 | 257 | 2017-08-07 | Send Friendship Walk Save the Date card | Staff Partner
| 35 | 243 | 2017-08-21 | Volunteer Kickoff: Send invitations to interested volunteers (consider including current committee members, sponsors, team captains, high dollar fundraisers and all prospect committee members | Event Chair/Co-Chair
| 35 | 243 | 2017-08-21 | 1 Team(s) (1% of goal) | All
| 35 | 243 | 2017-08-21 | $2,000.00 of Sponsorship (10% of goal) | All
| 35 | 243 | 2017-08-21 | $4,000.00 of Fundraising (5% of goal) | All
| 34 | 236 | 2017-08-28 | Team Recruitment Chair in place, Volunteer Commitment Form signed | Staff Partner/Event Chair
| 34 | 236 | 2017-08-28 | Team Retention Chair in place, Volunteer Commitment Form signed | Staff Partner/Event Chair
| 34 | 236 | 2017-08-28 | Publicty Chair in place, Volunteer Comitment Form signed | Staff Partner/Event Chair
| 34 | 236 | 2017-08-28 | Mission Chair in place, Volunteer Comitement Form signed | Staff Partner/Event Chair
| 34 | 236 | 2017-08-28 | Logistics Chair in place, Volunteer Comitment Form signed | Staff Partner/Event Chair
| 34 | 236 | 2017-08-28 | Review open chair positions on the Walk Planning Committee | Staff Partner/Event Chair
| 34 | 236 | 2017-08-28 | Volunteer Kickoff planning meeting with Chairs - set goals, determine: venue, date, time, format, speakers, invitations, etc. | Event Chair/Co-Chair
| 33 | 229 | 2017-09-04 | Train Chair positons | Event Chair/Co-Chair
| 33 | 229 | 2017-09-04 | Training schedule shared with all chair positions | Event Chair/Co-Chair
| 33 | 229 | 2017-09-04 | Share Frienship Walk resources with committee members | Event Chair/Co-Chair
| 33 | 229 | 2017-09-04 | Confirm date & location for Volunteer Kickoff | Event Chair/Co-Chair
| 33 | 229 | 2017-09-04 | Send/deliver invites for Volunteer Kickoff Party (3 weeks prior to event) | Event Chair/Co-Chair
| 33 | 229 | 2017-09-04 | Set meetings to renew last year's sponsors - Offer opportunity to increase level | Sponsorship Chair
| 33 | 229 | 2017-09-04 | Release Monthly Team Touch | Team Retention Chair
| 33 | 229 | 2017-09-04 | Start monthly Friendship Walk Committee meetings | Event Chair/Co-Chair
| 33 | 229 | 2017-09-04 | Have chairs complete their individual Sphere of Influence for Volunteer Kickoff Party invites | Event Chair/Co-Chair
| 33 | 229 | 2017-09-04 | Plan Committee Orientation - determine: date, time, venue, etc. | Event Chair/Co-Chair
| 32 | 222 | 2017-09-11 | Begin the New Team Tracking Spreadsheet | Team Recruitment Chair
| 32 | 222 | 2017-09-11 | Meetings with new sponsor targets | Sponsorship Chair
| 32 | 222 | 2017-09-11 | Reminder calls made to Volunteer Kickoff invitees (1-2 days prior) | Event Chair/Co-Chair
| 31 | 215 | 2017-09-18 | Host Volunteer Kickoff (7 months prior to Walk day) | Event Chair/Co-Chair
| 31 | 215 | 2017-09-18 | Create Walk Publicity plan (including emails, collateral, social media, public relations, ads, etc. | Staff Partner/Publicity Chair
| 31 | 215 | 2017-09-18 | Determine which items will be printed through the nationwide printing vendor, Vision | Staff Partner/Publicity Chair
| 31 | 215 | 2017-09-18 | Status check: Team Captain Stewardship Plan - Plan calls as Team Captains register | Team Retention/Team Recruitment Chair
| 31 | 215 | 2017-09-18 | Status Check: renewing past sponsors | Sponsorship Chair
| 30 | 208 | 2017-09-25 | Volunteer Kickoff follow-up: with all attendees, those who were unable to attend or were no shows and determine place for committee vacancies | Event Chair/Co-Chair
| 30 | 208 | 2017-09-25 | Send invitations for Friendship Walk Committee Orientation (1 week after Volunteer Kickoff event) | Event Chair/Co-Chair
| 30 | 208 | 2017-09-25 | Develop a stewardship plan for year-round recognition and continued promotion of high dollar fundraisers | Mission Chair
| 30 | 208 | 2017-09-25 | Permits confirmed/contracts signed for Walk event venue & route; insurance forms completed | Staff Partner/Logistics Chair
| 30 | 208 | 2017-09-25 | Plan and host a Spring Luncheon or special event for last year's high dollar fundraisers | Mission Chair
| 30 | 208 | 2017-09-25 | 5 Teams (5% of goal) | All
| 30 | 208 | 2017-09-25 | 50 Participants (5% of goal) | All
| 30 | 208 | 2017-09-25 | $2,000.00 of Sponsorship (10% of goal) | All
| 30 | 208 | 2017-09-25 | $5,600.00 of Fundraising (7% of goal) | All
| 29 | 201 | 2017-10-02 | Release Monthly Team Touch | Team Retention Chair
| 29 | 201 | 2017-10-02 | Plan & hold this month's Friendship Walk Committee meeting | Event Chair/Co-Chair
| 28 | 194 | 2017-10-09 | Reminder calls/email about Committee Orientation (1 week prior to CO) | Event Chair/Co-Chair
| 28 | 194 | 2017-10-09 | High dollar fundraisers Shout Outs on Social Media | Publicity Chair/Mission Chair
| 27 | 187 | 2017-10-16 | Host Friendship Walk Committee Orientation (2-4 weeks after Volunteer Kickoff) | Event Chair/Co-Chair
| 27 | 187 | 2017-10-16 | Status check: Team Captain Stewardship Plan - Plan calls as Team Captains register | Team Recruitment/Team Retention Chair
| 27 | 187 | 2017-10-16 | Status Check: renewing past sponsors | Sponsorship Chair
| 27 | 187 | 2017-10-16 | Finalize date/time/location for New Team Kickoff | Team Recruitment Chair
| 26 | 180 | 2017-10-23 | Status Check: Team Retention | Team Retention Chair
| 26 | 180 | 2017-10-23 | Meetings with new sponsor targets | Sponsorship Chair
| 26 | 180 | 2017-10-23 | Finalize media sponsors | Staff Partner/Publicity Chair
| 26 | 180 | 2017-10-23 | Develop new team recruitment target lists | Team Recruitment Chair
| 26 | 180 | 2017-10-23 | Hold one-on-one Committee Orientations for those who were unable to attend | Event Chair/Co-Chair
| 26 | 180 | 2017-10-23 | Design & Release collateral into the community | Staff Partner/Publicity Chair
| 26 | 180 | 2017-10-23 | Team Recruitment Committee develops plan for invitees to New Team Kickoff | Team Recruitment Chair
| 26 | 180 | 2017-10-23 | 10 Teams (10% of goal) | All
| 26 | 180 | 2017-10-23 | 100 Participants (10% of goal) | All
| 26 | 180 | 2017-10-23 | $10,000.00 of Sponsorship (50% of goal) | All
| 26 | 180 | 2017-10-23 | $6,400.00 of Fundraising (8% of goal) | All
| 25 | 173 | 2017-10-30 | Plan & hold this month's Friendship Walk Committee meeting | Event Chair/Co-Chair
| 25 | 173 | 2017-10-30 | Release Monthly Team Touch | Team Retention Chair
| 25 | 173 | 2017-10-30 | Plan & Finalize documents for Team Captain Kits | Staff Partner/Publicity Chair
| 24 | 166 | 2017-11-06 | High dollar fundraisers Shout Outs on Social Media | Publicity Chair/Mission Chair
| 24 | 166 | 2017-11-06 | Identify holes on committee and make a plan to fill gaps | Event Chair/Co-Chair
| 24 | 166 | 2017-11-06 | New Team Kickoff table host - Status Check | Team Recruitment Chair
| 24 | 166 | 2017-11-06 | Past Team Registration Event - Determine plan, time, format, etc. | Team Retention Chair
| 23 | 159 | 2017-11-13 | Team Captain Stewardship | Team Retention/Team Recruitment Chair
| 23 | 159 | 2017-11-13 | Status Check: renewing past sponsors | Sponsorship Chair
| 23 | 159 | 2017-11-13 | Finalize & send invitations for Past Team Registration Event - Past Team Captains for previous 3 years (4 weeks prior to event) | Team Retention Chair
| 22 | 152 | 2017-11-20 | Meetings with new sponsor targets | Sponsorship Chair
| 22 | 152 | 2017-11-20 | Hold second Volunteer Kickoff for team recruitment if needed | Team Recruitment Chair
| 22 | 152 | 2017-11-20 | Status Check: Team Retention | Team Retention Chair
| 22 | 152 | 2017-11-20 | Status Check: New Team Kickoff invitation list | Team Recruitment Chair
| 22 | 152 | 2017-11-20 | Post Past Team Registration Event information on Social Media | Staff Partner/Team Retention Chair
| 22 | 152 | 2017-11-20 | 15 Teams (15% of goal) | All
| 22 | 152 | 2017-11-20 | 130 Participants (13% of goal) | All
| 22 | 152 | 2017-11-20 | $12,600.00 of Sponsorship (63% of goal) | All
| 22 | 152 | 2017-11-20 | $7,200.00 of Fundraising (9% of goal) | All
| 21 | 145 | 2017-11-27 | Release Monthly Team Touch | Team Retention Chair
| 21 | 145 | 2017-11-27 | Print & assemble enough Team Captain Kits for the month (including enough for Past Team Registration Event) | Staff Partner/Publicity Chair
| 21 | 145 | 2017-11-27 | Past Team Registration Event RSVP Deadline (2 eeks prior to event) | Team Retention Chair
| 21 | 145 | 2017-11-27 | Follow-up calls to those who have not RSVPed to Past Team Registration Event | Team Retention Chair
| 20 | 138 | 2017-12-04 | High dollar fundraisers Shout Outs on Social Media | Publicity Chair/Mission Chair
| 20 | 138 | 2017-12-04 | Prepare & finalize poster & flier distribution plan | Publicity Chair
| 20 | 138 | 2017-12-04 | Determine sponsorship gap to goal plan | Sponsorship Chair
| 20 | 138 | 2017-12-04 | Plan & hold this month's Friendship Walk Committee meeting | Event Chair/Co-Chair
| 20 | 138 | 2017-12-04 | Status Check: New Team Kickoff Invitation list | Team Recruitment Chair
| 20 | 138 | 2017-12-04 | Finalize public relations & media materials plan & distribution plan | Publicity Chair
| 20 | 138 | 2017-12-04 | Table Host Status Check | Team Recruitment Chair
| 20 | 138 | 2017-12-04 | Email Past Team Registration Event Reminder | Staff Partner/Team Retention Chair
| 19 | 131 | 2017-12-11 | Make reminder calls for Past Team Registration Event (1-2 days prior to event) | Team Retention Chair
| 19 | 131 | 2017-12-11 | Host Past Team Registration Event (4 months prior to Walk day) | Team Retention Chair
| 19 | 131 | 2017-12-11 | Status check: Team Captain Stewardship Plan - Plan calls as Team Captains register | Team Recruitment/Team Retention Chair
| 18 | 124 | 2017-12-18 | Thank you for attending the Past Team Registration Event calls/notes & sorry we missed you calls/notes to no shows | Team Recruitment Chair
| 18 | 124 | 2017-12-18 | Status Check: Team Retention | Team Retention Chair
| 18 | 124 | 2017-12-18 | 20 Teams (20% of goal) | All
| 18 | 124 | 2017-12-18 | 150 Participants (15% of goal) | All
| 18 | 124 | 2017-12-18 | $15,000.00 of Sponsorship (75% of goal) | All
| 18 | 124 | 2017-12-18 | $8,000.00 of Fundraising (10% of goal) | All
| 17 | 117 | 2017-12-25 | Begin developing layout of the event site and Walk route/entertainment | Logistics Chair
| 17 | 117 | 2017-12-25 | Create event experience plan for Walk day | Logistics Chair
| 16 | 110 | 2018-01-01 | Print & assemple enough Team Captain Kits for the month | Staff Partner/Publicity Chair
| 16 | 110 | 2018-01-01 | Team Recruitment/Fundraising coaching call or mailing | Team Recruitment/Team Retention Chair
| 16 | 110 | 2018-01-01 | 40% of collateral (brochures, posters) out for distribution (Community Blitz Day) | Publicity Chair
| 16 | 110 | 2018-01-01 | Release final Monthly Team Touch | Team Retention Chair
| 16 | 110 | 2018-01-01 | Status Check: New Team Kickoff Invitation list | Team Retention Chair
| 16 | 110 | 2018-01-01 | Set up Internal Company/School/Community Kickoffs with your top 5-10 teams | Team Recruitment/Team Retention Chair
| 16 | 110 | 2018-01-01 | Plan & hold this month's Friendship Walk Committee meeting | Event Chair/Co-Chair
| 16 | 110 | 2018-01-01 | New Team Kickoff Planning - determine date, venue, time, secure speakers | Team Recruitment Chair
| 16 | 110 | 2018-01-01 | Gather a report of Walk day logistics needs (tent sizes, signage, tables, chairs, tents, staging, bathrooms, etc.) | Logistics Chair
| 16 | 110 | 2018-01-01 | Begin to recruit day of event volunteers | Logistics Chair
| 15 | 103 | 2018-01-08 | Begin to develop day of parking plan (traffic flow, VIP parking, overflow, etc.) | Logistics Chair
| 15 | 103 | 2018-01-08 | High dollar fundraisers Shout Outs on Social Media | Publicity Chair/Mission Chair
| 14 | 96 | 2018-01-15 | Status check: Team Captain Stewardship Plan - Plan calls as Team Captains register | Team Recruitment/Team Retention Chair
| 14 | 96 | 2018-01-15 | Status Check: Invitation Status Check | Team Recruitment Chair
| 13 | 89 | 2018-01-22 | Status Check on Team Retention numbers | Team Retention Chair
| 13 | 89 | 2018-01-22 | Begin planning for Challenge Week | Event Chair/Publicity Chair
| 13 | 89 | 2018-01-22 | New Team Kicoff Invites mailed (4 weeks prior to event) | Team Recruitment Chair
| 13 | 89 | 2018-01-22 | 35 Teams (35% of goal) | All
| 13 | 89 | 2018-01-22 | 200 Participants (20% of goal) | All
| 13 | 89 | 2018-01-22 | $20,000.00 of Sponsorship (100% of goal) | All
| 13 | 89 | 2018-01-22 | $12,000.00 of Fundraising (15% of goal) | All
| 12 | 82 | 2018-01-29 | Print & assemeble enough Team Captain Kits for the month (include enough for New Team Kickoff) | Staff Partner/Publicity Chair
| 12 | 82 | 2018-01-29 | Team Recruitment/Fundraising coaching call or mailing | Team Recruitment/Team Retention Chair
| 12 | 82 | 2018-01-29 | Next 40% of collateral (brochures, posters) out for distribution (Community Blitz Day #2) | Publicity Chair
| 12 | 82 | 2018-01-29 | Status Check: New Team Kickoff Invitation list | Team Recruitment Chair
| 12 | 82 | 2018-01-29 | Plan & hold this month's Friendship Walk Committee meeting | Event Chair/Co-Chair
| 12 | 82 | 2018-01-29 | New Team Kickoff event planning - speakers, script, ppt, slideshow, music, food, parking, etc. | Team Recruitment Chair
| 12 | 82 | 2018-01-29 | Being to hold your 5-10 Internal Kickoffs with large company/org teams | Team Recruitment/Team Retention Chair
| 12 | 82 | 2018-01-29 | Get staff and volunteers trained on taking Walk Day Donations | Staff Partner
| 11 | 75 | 2018-02-05 | High dollar fundraisers Shout Outs on Social Media | Publicity Chair/Mission Chair
| 11 | 75 | 2018-02-05 | RSVP deadline for New Team Kickoff (2 weeks prior to event) | Team Recruitment Chair
| 11 | 75 | 2018-02-05 | Follow-up calls to those who have not RSVPed to New Team Kickoff | Team Recruitment Chair
| 10 | 68 | 2018-02-12 | Status check: Team Captain Stewardship Plan - Plan calls as Team Captains register | Team Recruitment Chair/Team Retention Chair
| 10 | 68 | 2018-02-12 | Status Check: New Team Kickoff Invitation list | Team Recruitment Chair
| 10 | 68 | 2018-02-12 | Email New Team Kickoff Reminder (template in Luminate) | Staff Partner/Team Recruitment Chair
| 10 | 68 | 2018-02-12 | Plan and finalize Walk day VIF amenities | Mission Chair/Logistics Chair
| 10 | 68 | 2018-02-12 | Plan & finalize Walk day event experience elements | Logistics Chair
| 10 | 68 | 2018-02-12 | Fundraising Team Captain meeting/open house/conference call for all teams | Team Retention Chair
| 9 | 61 | 2018-02-19 | Make reminder calls for New Team Kickoff (1-2 days prior to event) | Team Recruitment Chair
| 9 | 61 | 2018-02-19 | Status Check: Team Retention | Team Retention Chair
| 9 | 61 | 2018-02-19 | Host New Team Kickoff (2 months prior to Walk day) | Team Recruitment Chair
| 9 | 61 | 2018-02-19 | Secure site and Walk route entertainment | Logistics Chair
| 9 | 61 | 2018-02-19 | 50 Teams (50% of goal) | All
| 9 | 61 | 2018-02-19 | 400 Participants (40% of goal) | All
| 9 | 61 | 2018-02-19 | $20,000.00 of Sponsorship (100% of goal) | All
| 9 | 61 | 2018-02-19 | $20,000.00 of Fundraising (25% of goal) | All
| 8 | 54 | 2018-02-26 | Thank you for attending the New Team Kicoff calls/notes & sorry we missed you calls/nots to no shows | Team Recruitment Chair
| 8 | 54 | 2018-02-26 | New Team Kickoff thank you calls to attendees | Team Recruitment Chair
| 8 | 54 | 2018-02-26 | Plan a Bank Night location & date. Finalize & send invitations (4 weeks prior to event) | Staff Partner
| 8 | 54 | 2018-02-26 | Begin arranging a safe, an on-site cash counting room and bank drop-off to secure Walk day cash donations | Logistics Chair
| 8 | 54 | 2018-02-26 | Finalize Walk day signage & order any additional signage & office supplies/materials | Staff Partner/Logistics Chair
| 8 | 54 | 2018-02-26 | Finalize registration flow | Staff Partner/Logistics Chair
| 7 | 47 | 2018-03-05 | Team Recruitment/Fundraising coaching call or mailing | Team Recruitment/Team Retention Chair
| 7 | 47 | 2018-03-05 | Print & assemble enough Team Captain Kits for the month | Staff Partner/Publicity Chair
| 7 | 47 | 2018-03-05 | Place day of event volunteers in roles, create Walk day schedule & make plans to host a volunteer training | Logistics Chair
| 7 | 47 | 2018-03-05 | Plan & hold this month's Friendship Walk Committee meeting | Event Chair/Co-Chair
| 6 | 40 | 2018-03-12 | Follow-up calls to all outstanding potential Team Captains | Team Recruitment Chair
| 6 | 40 | 2018-03-12 | High dollar fundraisers Shout Outs on Social Media | Publicity Chair/Mission Chair
| 6 | 40 | 2018-03-12 | Personal visits to potential Team Captains that did not attend a kickoff | Team Recruitment/Team Retention
| 6 | 40 | 2018-03-12 | Prepare mission activities/components for Walk day | Mission Chair/Logistics Chair
| 6 | 40 | 2018-03-12 | Secure emcee for the Walk day | Marketing & Outreach Chair/Logistics Chair
| 6 | 40 | 2018-03-12 | Identify & ask participants to speak on Walk day during opening ceremony | Marketing & Outreach Chair/Mission Chair
| 5 | 33 | 2018-03-19 | Ask the Event Chair & Vice Chair to write a letter to the editor | Marketing & Outreach Chair
| 5 | 33 | 2018-03-19 | Team Captain Engagement Plan calls as Team Captains register - Status Check | Team Retention Chair/Team Recruitment Chair
| 5 | 33 | 2018-03-19 | Finalize schedule for day of volunteers; fill any gaps | Logistics Chair
| 4 | 26 | 2018-03-26 | Final Status Check: Team Retention | Team Retention Chair
| 4 | 26 | 2018-03-26 | Fundraising Team Captain meeting/open house/conference call for all teams | Team Retention Chair
| 4 | 26 | 2018-03-26 | Call to all participants letting them know they are $X away from the next incentive program level | Team Recruitment Chair/Team Retention Chair
| 4 | 26 | 2018-03-26 | Identify potential Event Chair for next year | Staff Partner/Event Chair
| 4 | 26 | 2018-03-26 | Secure DJ for Walk day | Logistics Chair
| 4 | 26 | 2018-03-26 | Confirm Walk day water and food | Logistics Chair
| 4 | 26 | 2018-03-26 | Security confirmed for event | Staff Partner/Logistics Chair
| 4 | 26 | 2018-03-26 | Arrange for transportation of materials to site (signs, water, tents, etc.) | Logistics Chair
| 4 | 26 | 2018-03-26 | Release final 20% of all collateral (brochures, posters) | Marketing & Outreach Chair
| 4 | 26 | 2018-03-26 | Touch base calls to all Team Captains (4 weeks prior to Walk day) | Team Recruitment Chair/Team Retention Chair
| 4 | 26 | 2018-03-26 | Walk Celebration Party location & date set; finalize invitations | Team Retention Chair
| 4 | 26 | 2018-03-26 | Confirm all day of event volunteers; invite to pre-Walk day training, distrbute job descriptions & timeline to day of event volunteers | Logistics Chair
| 4 | 26 | 2018-03-26 | 80 Teams (80% of goal) | All
| 4 | 26 | 2018-03-26 | 600 Participants (60% of goal) | All
| 4 | 26 | 2018-03-26 | $20,000.00 of Sponsorship (100% of goal) | All
| 4 | 26 | 2018-03-26 | $48,000.00 of Fundraising (60% of goal) | All
| 3 | 19 | 2018-04-02 | Team Recruitment/Fundraising coaching call or mailing | Team Recruitment Chair/Team Retention Chair
| 3 | 19 | 2018-04-02 | Print & assemble enough Team Captain Kits for the month | Staff Partner/Publicity Chair
| 3 | 19 | 2018-04-02 | Plan & hold this month's Friendship Walk Committee meeting | Event Chair/Co-Chair
| 3 | 19 | 2018-04-02 | Develop Walk day vendor schedule and Walk day schedule | Logistics Chair
| 3 | 19 | 2018-04-02 | All speakers confirmed for opening ceremony | Mission Chair/Logistics Chair
| 3 | 19 | 2018-04-02 | Create and finalize a Walk day Social Media plan | Publicity Chair/Mission Chair
| 2 | 12 | 2018-04-09 | Opening ceremony script completed | Logistics Chair
| 2 | 12 | 2018-04-09 | Host day of event volunteer training | Logistics Chair
| 2 | 12 | 2018-04-09 | High dollar fundraisers Shout Outs on Social Media | Publicity Chair/Mission Chair
| 2 | 12 | 2018-04-09 | Last minute supply orders for Walk day | Logistics Chair
| 2 | 12 | 2018-04-09 | Bank Night reminder calls to all Team Captains (2 weeks prior to Walk day) | Team Recruitment/Team Retention
| 2 | 12 | 2018-04-09 | Host Bank Night (2 weeks prior to Walk day) | Team Recruitment/Team Retention
| 2 | 12 | 2018-04-09 | Finalize all mission components/activities for Walk day | Mission Chair/Logistics Chair
| 2 | 12 | 2018-04-09 | Confirm sponsor elements - banners, tents, tables, etc. | Sponsorship Chair/Logistics Chair
| 2 | 12 | 2018-04-09 | Finalize all activities, team photo area, VIF tent, kids zone, etc. | Logistics Chair
| 2 | 12 | 2018-04-09 | Final opening ceremony script delivered to emcee, DJ, speakers & stage manager | Logistics Chair
| 1 | 5 | 2018-04-16 | Status check: Team Captain Stewardship Plan - Plan calls as Team Captains register | Team Retention/Team Recruitment Chair
| 1 | 5 | 2018-04-16 | Pack for Walk day | Logistics Chair
| 1 | 5 | 2018-04-16 | Logistics calls to all Team Captains (1 week prior to Walk day) | Logistics Chair/Team Recruitment
| 1 | 5 | 2018-04-16 | Logistics email to all participants - 2 days prior to Walk day | Staff Partner/Logistics Chair
| 1 | 5 | 2018-04-16 | Calls to confirm event & Walk route entertainment | Logistics Chair
| 1 | 5 | 2018-04-16 | Reminder calls to sponsors inviting them to Walk day | Sponsorship Chair
| 1 | 5 | 2018-04-16 | Reminder calls to all Walk day vendors | Logistics Chair
| 1 | 5 | 2018-04-16 | Event site & Walk route final walk through | Staff Partner/Event Chair/Logistics Chair
| 1 | 5 | 2018-04-16 | Order thank you gifts for all Walk Planning Committee members | Staff Partner
| Walk Day | 0 | 2018-04-21 | Have an amazing Walk day and find time to take a moment to enjoy all your hard work | All
| Walk Day | 0 | 2018-04-21 | Announce Walk Celebration Party date | Event Chair
| Walk Day | 0 | 2018-04-21 | 100 Teams (100% of goal) | All
| Walk Day | 0 | 2018-04-21 | 800 Participants (80% of goal) | All
| Walk Day | 0 | 2018-04-21 | $20,000.00 of Sponsorship (100% of goal) | All
| Walk Day | 0 | 2018-04-21 | $64,000.00 of Fundraising (80% of goal) | All
| 0 | -2 | 2018-04-23 | Send out Walk Celebration Party invitations | Staff Partner/Team Retention Chair
| 0 | -2 | 2018-04-23 | Enter Walk day registrations and donations | Staff Partner
| 0 | -2 | 2018-04-23 | Write thank you notes and place in the mail to all Walk Planning Committee members | Staff Partner/Event Chair
| 0 | -2 | 2018-04-23 | Send a post-event thank you to day of volunteers | Logistics Chair
| 0 | -2 | 2018-04-23 | Send post-event survey to all participants | Head Quarters
| 0 | -2 | 2018-04-23 | Thank you calls to all Team Captains | Team Retention Chair
| 0 | -2 | 2018-04-23 | Send out thank you postcard to all walkers | Staff Partner/Event Chair
| -1 | -9 | 2018-04-30 | Check and communicate with your local National Teams who qualify for special incentives or matching gifts | Staff Partner
| -1 | -9 | 2018-04-30 | Post-event special thank you to your top teams | Event Chair/Team Retention Chair
| -1 | -9 | 2018-04-30 | Post-event recognition to high dollar fundraisers | Event Chair/Mission Committee
| -2 | -16 | 2018-05-07 | Call to all participants letting them know they are $X away from the next incentive program level and the fundraising deadline to qualify for incentive prizes. | Team Recruitment/Team Retention
| -2 | -16 | 2018-05-07 | High dollar fundraisers Shout Outs on Social Media | Publicity Chair/Mission Chair
| -2 | -16 | 2018-05-07 | Walk Planning Committee Debrief Meeting - plan for gap to goal if necessary, Walk Celebration Party planning | Staff Partner/Event Chair
| -2 | -16 | 2018-05-07 | Finalize sponsorship thank you gifts & make thank you calls to all sponsors | Sponsorship Chair
| -2 | -16 | 2018-05-07 | Ask Friendship Walk Committee to complete their feedback survey forms | Event Chair/Co-Chair
| -2 | -16 | 2018-05-07 | Determine who will be receiving awards at the Walk Celebration Party. Gifts/trophies ordered? | Team Retention Chair
| -3 | -23 | 2018-05-14 | Schedule Proof of Performance meetings | Sponsorship Chair
| -3 | -23 | 2018-05-14 | Reminder email about Walk Celebration Party | Team Retention Chair
| -4 | -30 | 2018-05-21 | Analyze post-event survey results | Staff Partner/Event Chair/Co-Chair
| -4 | -30 | 2018-05-21 | Vendor to fulfill fundraising incentive program prizes (30 days post-event) | Staff Partner
| -4 | -30 | 2018-05-21 | Secure outstanding matching gifts | Team Recruitment/Team Retention
| -4 | -30 | 2018-05-21 | Reminder calls about Walk Celebration party (1-2 days prior to event) | Team Retention Chair
| -4 | -30 | 2018-05-21 | Host Walk Celebration Party (1 month after Walk day) | Team Retention Chair
| -4 | -30 | 2018-05-21 | Evaluate your Walk's end of the year KPI's to help develop stratey for next year | Staff Partner/Event Chair
| -4 | -30 | 2018-05-21 | 100 Teams (100% of goal) | All
| -4 | -30 | 2018-05-21 | 1000 Participants (100% of goal) | All
| -4 | -30 | 2018-05-21 | $20,000.00 Teams (100% of goal) | All
| -4 | -30 | 2018-05-21 | $80,000.00 of Fundraising (100% of goal) | All
| -5 | -37 | 2018-05-28 | 45 Day Report | Staff Partner
| -5 | -37 | 2018-05-28 | Thank you to those who attended Walk Celebration Party and sorry we missed you to those who were unable to attend | Team Retention Chair
Formulas:
Friendship Walk: = E4-[Days Prior]
Friendship Walk: = E4-[Days Prior, row below]

## Sheet2
Noel | 11
Add important dates (NTK, Bank Night, etc.) to website | 11
Customize website | 11
Update Walk website with Walk details | 10
Coathing emails | 10
Setting up EMC/Text to Donate | 10
Recruitment emails | 10
10
10
10
10
10
10
10
10
10
10
Walk Team | 9
Order materials for TC kits | 9
submit event insurance | 9
Securing day of elements: Speakers, PG reps, tents, security, entertainment, etc. | 9
Press releases | 9
TC Workshop/Bootcamp | 9
Order T-shirts | 9
Regional Training | 9
Secure water | 9
Challenge Week | 9
Mail sponsorship invoices | 9
Order directional signs | 9
Order mission signs for route | 8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
5
5
5
5
5
5
5
5
5
5 Months Prior to Walk Katie
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
4 Months Prior to Walk Katie
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
3
3
3
3
3
3 Months Prior to Walk Katie
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
2
2
2
2 Months Prior to Walk Darby
2
2
2
1
1
1
1
1
1
1
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
1
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-1
-2